## Future Work
CrewLogic Future-Work Register - stable IDs FW-01..FW-51 (do NOT renumber) - 2026-07-05 ¦ 12 Done, 5 Partial, 3 Dropped, 31 Open ¦ +FW-67 added 2026-08-16 (Recycling manual-revenue; note: FW-52..66 allocated outside this file)
ID | Area | Item | What it is | State / Next step | Priority | Status | Notes (verified evidence)
FW-01 | Telematics / Trucks | Linxup live end-to-end validation | The Motive/Linxup consolidation + Linxup webhook shipped in v5.50.0, but the live Linxup path was never exercised. | Prod Linxup franchise 209f31ef has cameras/devices offline; validate when back online by generating the token in Settings->Trucks and pasting URL+token into their Linxup webhook. |  | Not started | Receiver deployed; live path unexercised — prod Linxup franchise 209f31ef cameras offline (hardware-blocked).
FW-02 | Telematics / Trucks | Linxup job-level arrive/leave matching | Phase-1 covers fence-name alerts only, not job-level arrive/leave. | Needs Linxup geofence-create; explicit follow-on. |  | Not started | crewlogic-geofence-create hard-rejects non-Motive (index.ts:130); Linxup geofence-create not built.
FW-03 | Telematics / Trucks | Re-enter Motive token in prod Settings | Per-franchise telematics creds live in Vault and don't carry dev->prod. | Owner re-enters the #90 Motive token in prod Settings->Trucks and validates trucks+jobs on prod. |  | Done | VERIFIED DONE 2026-07-05 — prod #90 Motive already set up: pull token connected (3 trucks, telematics_credentials is_active) + webhook secret configured (motive_webhook_config). Migration 0033 preserved it; re-entry was never actually needed. (Prod validation stamp June 12; re-save on app.crewlogicai.com to refresh — optional.)
FW-04 | Telematics / Trucks | Refine dashcam/fault-code event labels | Geofence alerts auto-capture dashcam-disconnect and fault-code events generically. | Refine the labels when each type is first seen live. |  | Not started | crewlogic-motive-webhook stores fault/dashcam events generically (index.ts:116); refine labels when first seen.
FW-05 | Telematics / Trucks | Optional 'N trucks on site' count | A live count of trucks currently at a job site was scoped but deferred. | Not built. |  | Not started | No on-site-count code exists (grep clean); deferred.
FW-06 | Telematics / Trucks | Telematics partnership / referral links | Explore a Motive/Linxup referral deal since CrewLogic funnels GPS signups. | Hook in place (plain vendor links); swap for referral URLs when they exist. |  | Not started | Links still plain gomotive.com/linxup.com (index.html:7854-55,11271-72); owner business action.
FW-07 | Maps / Dispatch / Routing | Estimates Desk iCal calendar lane (Chunk 4) | The Estimates Desk shipped (v5.48.4) without its planned iCal calendar lane. | Deferred. |  | Not started | Estimates Desk shipped w/o iCal; no .ics/VEVENT code anywhere.
FW-08 | Maps / Dispatch / Routing | Per-appointment Vonigo cancel | Cancelling one appointment on a multi-appointment Vonigo job currently just blocks, since per-appointment WO-cancel isn't achievable by API probing. | Parked pending a Vonigo support ticket; wire the correct cancel-by-woID call when they return it. |  | Not started | Multi-appt cancel still blocks + routes to Vonigo grid; cancel-by-woID not wired (Vonigo ticket pending).
FW-09 | Maps / Dispatch / Routing | Real route optimization | Recombine the day's booked jobs across routes to minimize drive time (suggest-only, needs a customer call first). | Marked brainstorm-before-building; act-now plumbing = reusable move/availability/job-read server tools returning geocoded lat/lon + duration. |  | Partial | Geocoded server tools EXIST (crewlogic-dispatch geocode/listRouteJobs/suggestSlots/moveJob); cross-route recombine engine not built.
FW-10 | Maps / Dispatch / Routing | In-app reschedule ('pull it forward') | Move a job's appointment from inside CrewLogic when a truck is near a job scheduled days out. | Not started; needs open-slot visibility, a date/time picker on the job popup, and a Vonigo WorkOrder write. |  | Dropped | KILLED by owner 2026-07-05 — not pursuing (desktop drag-move + voice move already cover this).
FW-11 | Maps / Dispatch / Routing | Route Optimizer Round-2 ideas | R1 disposal-stop recommender is live; Round-2 features are unbuilt. | geofence wait-time accrual, Google-Sheet bulk import, AI cost-vs-time recommendation, recycling/donation hours mirroring. |  | Not started | None shipped: disposalWait still static global; no sheet import; no AI cost-vs-time rec; recycling/donation hours not mirrored.
FW-12 | Maps / Dispatch / Routing | Route Optimizer multi-tenant re-architecture | The #90 route engine still runs on n8n + the owner's personal Google Sheet and is hard-gated to franchise 90. | Move to edge functions + Supabase tables before any other franchisee (blocks it as a paid Enterprise feature). |  | Not started | optimizeRoute() still calls n8n /crewlogic-route (index.html:11598); not migrated to edge fns/tables.
FW-13 | Maps / Dispatch / Routing | Per-facility wait times | A single global wait-time applies to all disposal/recycling/donation sites; owner wants per-site values in Cost->Facilities. | Likely a wait_time column + per-site input feeding route/cost math, with the global value backfilled as each site's default. |  | Not started | Single global disposalWait; facilities table (0023) has no wait column; no per-site input.
FW-14 | Maps / Dispatch / Routing | Weather alerts: narrow scope + trucks screen | NWS weather alerts are state-level and shown only on the dashboard + Job Plan. | Narrow to the office point; surface on the trucks screen. |  | Dropped | KILLED by owner 2026-07-05 — not needed (state-level weather on dashboard + Job Plan is sufficient).
FW-15 | Maps / Dispatch / Routing | Voice command: move job between routes | A separate row for voice->AI->Vonigo job-route reassignment. | Still listed 'Not started', overlapping the since-shipped Voice AI Dispatcher move-by-voice. |  | Done | VERIFIED DONE — voice move-with-route shipped (crewlogic-dispatch -> Vonigo method16; dispatch/index.ts:453,522).
FW-16 | Maps / Dispatch / Routing | Voice Dispatcher: prod write + voice-bar popup | The Voice AI Dispatcher is live, but the move/cancel/duration WRITE path is only read-verified. | Owner runs a real command; also mirror the unified conversation popup on the Manage Jobs voice bar. |  | Done | VERIFIED DONE — owner confirms the dispatcher write path (move/cancel/duration) works in prod, 2026-07-05.
FW-17 | Maps / Dispatch / Routing | Town title-case on job alerts | Job-alert towns render UPPERCASE from Vonigo (e.g. FALL RIVER). | A quick display tweak if wanted. |  | Done | VERIFIED DONE (prod v5.50.2, 2026-07-05) — town/city title-cased on job ALERTS (_geofenceAlertRow) AND the schedule board (job chip + hover/sticky popup City row) via _titleCaseTown. Client names untouched. Other surfaces (price-lookup, customer list) intentionally left as-is.
FW-18 | Pricing / CRM / Vonigo | Vonigo date-range CRM pipeline | Pull leads, estimates, cancellations, cases, and UCBs from Vonigo by date range into a CRM-style pipeline so nothing slips. | Not started; open questions: define 'UCB,' endpoint mapping per category, pull cadence. |  | Not started | No date-range CRM pipeline; only crewlogic-todays-workorders (today-only). Bigger project.
FW-19 | Pricing / CRM / Vonigo | National Accounts auto-fill job Summary | Enterprise/JL-only: AI-simplify the customer warning (<=60 words) and write it to each NA job's Vonigo Summary field. | Research done, nightly-cron trigger decided; build not started. |  | Not started | Vonigo write path proven, but simplify-prompt + nightly cron not built; no NA/summary cron.
FW-20 | Pricing / CRM / Vonigo | Vonigo submit server-side null-price guard | v5.49.1 added the frontend guard that auto-heals/aborts on charges missing a priceItemID. | Optional server-side guard in crewlogic-estimate deferred. |  | Partial | Frontend guard live (v5.49.1); handleSubmitQuote has NO server-side null-priceItemID rejection — server guard deferred.
FW-21 | Pricing / CRM / Vonigo | Deploy native CPL fix to prod | CPL per-item discounting for native price books was fixed on dev (v5.38.0), native-only/dev-only. | Pending owner UI validation and a prod deploy of crewlogic-pricing. |  | Done | VERIFIED DONE — CPL fix on main (v5.50.0, f0c32f7) + prod crewlogic-pricing returns blockType (downloaded+checked). Hub 'pending' was stale.
FW-22 | Pricing / CRM / Vonigo | Shed/building estimator undercounts volume | The shed/building volume estimator computes ~half the actual volume. | Not started; add floor-joist depth, roof-joist depth, and shingle-layer inputs, verified against a known shed. |  | Done | VERIFIED DONE (prod v5.50.2, 2026-07-05) — calcShed rewritten: walls + floor + PITCHED roof debris volume with floor-joist / roof-rafter / shingle-layer inputs + on-screen walls/floor/roof breakdown (fixes the missing-roof undercount). Owner-tested/approved. Thickness factors remain calibratable if field use shows drift.
FW-23 | Pricing / CRM / Vonigo | Route-Optimizer/Storage 16 cy quick-buttons | Four Route-Optimizer/Storage quick-select buttons hardcode 16 cy. | Cosmetic open item under Stage A native pricing. |  | Not started | Four buttons still hardcode 16 cy (index.html 3457,3466,3607,3616). Cosmetic.
FW-24 | Native mode / Onboarding | Onboarding: serviceStates + estimator default state | Capture the franchise's serviceStates and a per-estimator default state at signup/provisioning, owner-editable in Settings. | Not started; feeds Town Price Lookup. |  | Dropped | KILLED by owner 2026-07-05 — native users already enter ZIPs in pricing; redundant.
FW-25 | Native mode / Onboarding | New-estimate onboarding prompt | A native owner starting a first estimate with no ZIPs/customers expected a prompt to add ZIPs and import customers first. | Not started; add a first-run/empty-state guide. |  | Not started | No first-run empty-state prompt (add ZIPs/import customers) exists.
FW-26 | Native mode / Onboarding | Native price-book onboarding finishers | The 'set up your price book' prompt is partly done. | Pending: the orange home Price Lookup tile for price-book-less native owners (needs a hasPriceBook signal) + the empty-default-list UX. |  | Partial | Friendly 'no price book' notice DONE; orange home Price Lookup tile NOT built (no hasPriceBook signal).
FW-27 | Native mode / Onboarding | Phase 2 onboarding wizard | The marketing/trial two-URL split is live; the Phase 2 onboarding wizard remains. | Not built. |  | Not started | Two-URL split done/live; Phase 2 onboarding wizard has no code.
FW-28 | Settings / UX | Streamline the Settings environment | Owner: 'the whole settings environment is a mess, need to streamline it... later.' | A bigger UX/reorg pass; not started. |  | Not started | No Settings reorg done; owner backlog 'the whole settings environment is a mess... later.'
FW-29 | Settings / UX | Hide unused home cards | Reorderable home cards are live. | Optional follow-up: let users hide cards they don't use. Not built. |  | Not started | Reorder IS live (SortableJS, 0021); HIDE logic does not exist.
FW-30 | Settings / UX | index.html size / architecture review | The single ~22k-line index.html keeps growing. | Deliberate keep-single-file vs light-split/build decision; queued for strategy mode; any split must preserve the no-build Cloudflare Pages deploy. |  | Not started | Decision not made; file ~22k lines; keep-single-file vs split undecided.
FW-31 | Payments / Billing | Payments + pricing model | Accept card transactions and design a location-billed seats x feature-gates + per-tier AI-allowance model on greenfield Stripe. | In planning; docs/plan-payments.md drafted awaiting approval, then build dev-first. |  | Done | VERIFIED DONE (build) — billing built + shipped DORMANT: crewlogic-billing (Stripe checkout/portal/webhook), paywall tier picker, migrations 0025/0026. Hub 'build not started' was WRONG. Activation = item #39.
FW-32 | Payments / Billing | Billing activation | Round-1 billing shipped to prod dormant (BILLING_ENABLED off). | Apply migration 0025 to prod + set up LIVE-mode Stripe before flipping BILLING_ENABLED (then ENFORCE_TRIAL). |  | Not started | Dormant by design — BILLING_ENABLED=IS_DEV_ENV (prod OFF); flip + LIVE Stripe + apply 0025 to prod remain.
FW-33 | Payments / Billing | Subscription field-model code finishers | Two code finishers to land with Payments. | Stop reading franchise subscription_tier as an access grant; write 'free' (not null) in provisionNative. |  | Done | VERIFIED DONE (superseded) — gate logic now never lets 'free' tier override an access-granting tenant (index.html:5316, oauth-callback:490); provisionNative writes null intentionally. 'Write free' ask moot.
FW-34 | Payments / Billing | Trial-expiry UX questions | Parked: what happens at 14-day trial end, messaging, lockout, re-enable without losing settings. | Code read suggests ENFORCE_TRIAL is currently false and settings persist; verify before answering definitively. |  | Partial | Countdown banner + trialState shipped (non-blocking copy); ENFORCE_TRIAL=false — end-of-trial lockout/re-enable UX decisions remain.
FW-35 | Auth / Session | Truly-dead session 'Reconnecting...' banner | Silent auto-refresh is live for the stale-but-refreshable case. | Deferred: a soft 'Reconnecting...' banner + one-tap re-auth for the rare truly-dead session. |  | Not started | One silent refresh then clean re-auth redirect; no soft 'Reconnecting...' banner / one-tap re-auth.
FW-36 | Auth / Session | Harden crewlogic-trucks caller verification | Per-request caller verification is deferred because Google-OAuth owners have no Supabase JWT. | Folded into future unified-auth work; residual risk low. |  | Not started | crewlogic-trucks uses service-role RPC, CORS '*', no per-request caller/JWT/ownership check.
FW-37 | Auth / Session | 'Name your workspace' mis-route check | The workspace-naming trap got a clearer label (live). | Low-priority: investigate whether a fully provisioned account can mis-route there via a profile-lookup edge case. |  | Done | VERIFIED DONE — showNameWorkspaceScreen only on no-profile+no-invite; buildSessionFromSupabaseAuth retries once on incomplete profile.
FW-38 | Auth / Session | Native toolbar-fix prod promote | The native-estimate reopen toolbar bug is fixed and owner-verified on dev. | Pending prod promote. |  | Done | VERIFIED DONE — renderChargeRows->renderCharges fix on MAIN at v5.50.0 (836f993). Hub 'pending prod promote' was stale.
FW-39 | Multi-tenant / Time zones | Generalize Eastern-hardcoded date logic | The dispatcher is tz-aware now, but two spots stay Eastern-hardcoded. | crewlogic-todays-workorders day-window + crewlogic-job-plan nowET; apply the existing tz pattern before any non-ET franchise relies on them. |  | Not started | Both still Eastern-hardcoded: todays-workorders getEasternMidnightEpoch + job-plan nowET; no resolveTimezone/STATE_TZ.
FW-40 | Multi-tenant / Time zones | Onboarding: capture location + confirm timezone | Have the franchisee enter full office location and confirm their IANA timezone at onboarding (cost_settings.officeTimezone). | Not started; until then each non-ET franchise needs a manual officeTimezone backfill. |  | Not started | officeTimezone only READ, never written; onboarding/settings capture officeState only.
FW-41 | Infra / Deploy | Reconnect crewlogic-marketing Pages Git | A Cloudflare account change left the Pages projects Git-disconnected; crewlogic is reconnected. | crewlogic-marketing (crewlogicai.com) likely still needs the same Git reconnect. |  | Not started | Owner Cloudflare action — app project reconnected; crewlogic-marketing still needs Git reconnect.
FW-42 | Infra / Deploy | Retire the last n8n dependency | Only the route-optimization engine still runs in n8n. | Retiring it is tied to the Route Optimizer re-architecture. |  | Not started | N8N_BASE + apiFetch('/crewlogic-route') still live (index.html:3962,11598); route engine unchanged on n8n.
FW-43 | Infra / Deploy | Estimate-charges normalization (Phases 4-5) | Line items still live in the payload.charges JSON blob; normalization tables + dual-write are dev-only. | Apply migrations 0012+0013 + deploy dual-write to prod, then cut reads over (Phase 4) and retire the blob (Phase 5). |  | Partial | Dual-WRITE shipped (crewlogic-estimate mirrors into estimate_charges); ZERO reads yet + prod-apply 0012/0013 + retire blob remain.
FW-44 | Infra / Deploy | Storage headroom / STORAGE_INCLUDED_GB | Prod is on Supabase free tier and the secret isn't set, so the usage dashboard defaults to 1 GB. | Set the prod secret to 100 when moving to Supabase Pro; watch estimate-photo storage as testers onboard. |  | Not started | Owner action — prod STORAGE_INCLUDED_GB unset (dashboard defaults 1GB); set to 100 on Supabase Pro.
FW-45 | Infra / Deploy | estimate-photos per-franchise path scoping | RLS is enforced, but per-franchise storage path scoping is deferred. | A fuller cross-tenant test suite also remains as a Phase 3 RLS follow-up. |  | Not started | Upload path already per-franchise; RLS bucket-scoped only (0011) — path-level scoping deferred.
FW-46 | Security | Rotate + strip committed API keys | docs/Route Optimization.json embeds live Google Maps, Anthropic (x2), and Motive keys. | Rotate the exposed keys and strip the file (HEAD removal is the ceiling on this private repo). |  | Done | VERIFIED DONE 2026-07-05 — export redacted to MY_* placeholders + real-key backup deleted; verified not in repo/history/index; owner confirms the file never synced/shared → keys never left the machine, no rotation needed.
FW-47 | Security | Google Cloud credentials cleanup | Consolidate all CrewLogic Google keys/OAuth clients into one project and delete the unused sprawl. | Not started (inventory done); referrer/IP-restricted keys, repoint secrets, proxy Street View through an edge fn. |  | Not started | Street View still client-side hardcoded STREET_VIEW_KEY (no edge-fn proxy); keys split across projects, no consolidation.
FW-48 | Analytics | Track Photo-Analyzer volume-tier adjustments | Record when a user bumps an estimate up/down a tier after the AI Photo Analyzer, to measure and correct its bias. | Not started; plan first (usage_events vs dedicated table, AI-only scope, store raw suggested CY?). |  | Not started | Tier overrides stored client-side only; no analytics event on post-analyzer tier bump.
FW-49 | Analytics | Deferred usage-metering events | Metering is live, but Street View metering (needs the server proxy) and price.lookup/estimate.created events were deferred. | These extend the billing/cost backbone. |  | Not started | usage.ts emits ai.*/maps.* only; no price.lookup/estimate.created/Street-View metering.
FW-50 | Provisioning validation (QA) | Live Vonigo-connect prod validation | The two @junkluggers.com provisioning cells (invite + marketing) were never run end-to-end in prod. | Validate on a real onboarding: user -> Vonigo-pending profile -> enter creds -> franchise attaches under the JL tenant with no paywall (marketing cell carries the 14-day clock). |  | Not started | Runtime — provisioning cells exist in code; no evidence the 2 @junkluggers.com cells were run end-to-end in prod.
FW-51 | Provisioning validation (QA) | Confirm-email deliverability re-test | DMARC is added (SPF/DKIM pass), fixing junk-foldering. | A real signup re-test to confirm inbox delivery; a custom Supabase auth domain stays deferred (paid). |  | Done | VERIFIED DONE — owner tested confirm-email inbox delivery, working 2026-07-05 (DMARC/SPF/DKIM).
FW-67 | Recycling / Revenue | Manual recycling-revenue entry (un-geofenced trips) | Recycling revenue is captured ONLY for geofence-derived visits (geofence exit dwell -> visit -> settle amount). Trips where the truck never triggered the recycling geofence (device unplugged, GPS gap, facility not geofenced, dwell too short) have NO visit row, so that revenue is uncounted. | Backlog (owner 2026-08-16). Add an "Add trip / manual entry" path on the Recycling screen (date, truck/route, facility, amount+weight, no geofence backing, flagged manual). Draft a contract addendum (manual-entry data model + dedupe rule) for sign-off BEFORE code. |  | Not started | Extends docs/contract-recycling-revenue.md (approved geofence-visit model). Brief: docs/plan-recycling-manual-revenue.md. KEY RISK: dedupe if a delayed geofence visit later appears for the same trip (merge by facility+date+truck, or manual link).