## Future Work
CrewLogic - Identified Future Work (from .HUB/Hub.md) - 2026-07-05
# | Area | Item | What it is | State / Next step | Priority | Status | Notes
1 | Telematics / Trucks | Linxup live end-to-end validation | The Motive/Linxup consolidation + Linxup webhook shipped in v5.50.0, but the live Linxup path was never exercised. | Prod Linxup franchise 209f31ef has cameras/devices offline; validate when back online by generating the token in Settings->Trucks and pasting URL+token into their Linxup webhook.
2 | Telematics / Trucks | Linxup job-level arrive/leave matching | Phase-1 covers fence-name alerts only, not job-level arrive/leave. | Needs Linxup geofence-create; explicit follow-on.
3 | Telematics / Trucks | Re-enter Motive token in prod Settings | Per-franchise telematics creds live in Vault and don't carry dev->prod. | Owner re-enters the #90 Motive token in prod Settings->Trucks and validates trucks+jobs on prod.
4 | Telematics / Trucks | Refine dashcam/fault-code event labels | Geofence alerts auto-capture dashcam-disconnect and fault-code events generically. | Refine the labels when each type is first seen live.
5 | Telematics / Trucks | Optional 'N trucks on site' count | A live count of trucks currently at a job site was scoped but deferred. | Not built.
6 | Telematics / Trucks | Telematics partnership / referral links | Explore a Motive/Linxup referral deal since CrewLogic funnels GPS signups. | Hook in place (plain vendor links); swap for referral URLs when they exist.
7 | Maps / Dispatch / Routing | Estimates Desk iCal calendar lane (Chunk 4) | The Estimates Desk shipped (v5.48.4) without its planned iCal calendar lane. | Deferred.
8 | Maps / Dispatch / Routing | Per-appointment Vonigo cancel | Cancelling one appointment on a multi-appointment Vonigo job currently just blocks, since per-appointment WO-cancel isn't achievable by API probing. | Parked pending a Vonigo support ticket; wire the correct cancel-by-woID call when they return it.
9 | Maps / Dispatch / Routing | Real route optimization | Recombine the day's booked jobs across routes to minimize drive time (suggest-only, needs a customer call first). | Marked brainstorm-before-building; act-now plumbing = reusable move/availability/job-read server tools returning geocoded lat/lon + duration.
10 | Maps / Dispatch / Routing | In-app reschedule ('pull it forward') | Move a job's appointment from inside CrewLogic when a truck is near a job scheduled days out. | Not started; needs open-slot visibility, a date/time picker on the job popup, and a Vonigo WorkOrder write.
11 | Maps / Dispatch / Routing | Route Optimizer Round-2 ideas | R1 disposal-stop recommender is live; Round-2 features are unbuilt. | geofence wait-time accrual, Google-Sheet bulk import, AI cost-vs-time recommendation, recycling/donation hours mirroring.
12 | Maps / Dispatch / Routing | Route Optimizer multi-tenant re-architecture | The #90 route engine still runs on n8n + the owner's personal Google Sheet and is hard-gated to franchise 90. | Move to edge functions + Supabase tables before any other franchisee (blocks it as a paid Enterprise feature).
13 | Maps / Dispatch / Routing | Per-facility wait times | A single global wait-time applies to all disposal/recycling/donation sites; owner wants per-site values in Cost->Facilities. | Likely a wait_time column + per-site input feeding route/cost math, with the global value backfilled as each site's default.
14 | Maps / Dispatch / Routing | Weather alerts: narrow scope + trucks screen | NWS weather alerts are state-level and shown only on the dashboard + Job Plan. | Narrow to the office point; surface on the trucks screen.
15 | Maps / Dispatch / Routing | Voice command: move job between routes | A separate row for voice->AI->Vonigo job-route reassignment. | Still listed 'Not started', overlapping the since-shipped Voice AI Dispatcher move-by-voice.
16 | Maps / Dispatch / Routing | Voice Dispatcher: prod write + voice-bar popup | The Voice AI Dispatcher is live, but the move/cancel/duration WRITE path is only read-verified. | Owner runs a real command; also mirror the unified conversation popup on the Manage Jobs voice bar.
17 | Maps / Dispatch / Routing | Town title-case on job alerts | Job-alert towns render UPPERCASE from Vonigo (e.g. FALL RIVER). | A quick display tweak if wanted.
18 | Pricing / CRM / Vonigo | Vonigo date-range CRM pipeline | Pull leads, estimates, cancellations, cases, and UCBs from Vonigo by date range into a CRM-style pipeline so nothing slips. | Not started; open questions: define 'UCB,' endpoint mapping per category, pull cadence.
19 | Pricing / CRM / Vonigo | National Accounts auto-fill job Summary | Enterprise/JL-only: AI-simplify the customer warning (<=60 words) and write it to each NA job's Vonigo Summary field. | Research done, nightly-cron trigger decided; build not started.
20 | Pricing / CRM / Vonigo | Vonigo submit server-side null-price guard | v5.49.1 added the frontend guard that auto-heals/aborts on charges missing a priceItemID. | Optional server-side guard in crewlogic-estimate deferred.
21 | Pricing / CRM / Vonigo | Deploy native CPL fix to prod | CPL per-item discounting for native price books was fixed on dev (v5.38.0), native-only/dev-only. | Pending owner UI validation and a prod deploy of crewlogic-pricing.
22 | Pricing / CRM / Vonigo | Shed/building estimator undercounts volume | The shed/building volume estimator computes ~half the actual volume. | Not started; add floor-joist depth, roof-joist depth, and shingle-layer inputs, verified against a known shed.
23 | Pricing / CRM / Vonigo | Route-Optimizer/Storage 16 cy quick-buttons | Four Route-Optimizer/Storage quick-select buttons hardcode 16 cy. | Cosmetic open item under Stage A native pricing.
24 | Native mode / Onboarding | Onboarding: serviceStates + estimator default state | Capture the franchise's serviceStates and a per-estimator default state at signup/provisioning, owner-editable in Settings. | Not started; feeds Town Price Lookup.
25 | Native mode / Onboarding | New-estimate onboarding prompt | A native owner starting a first estimate with no ZIPs/customers expected a prompt to add ZIPs and import customers first. | Not started; add a first-run/empty-state guide.
26 | Native mode / Onboarding | Native price-book onboarding finishers | The 'set up your price book' prompt is partly done. | Pending: the orange home Price Lookup tile for price-book-less native owners (needs a hasPriceBook signal) + the empty-default-list UX.
27 | Native mode / Onboarding | Phase 2 onboarding wizard | The marketing/trial two-URL split is live; the Phase 2 onboarding wizard remains. | Not built.
28 | Settings / UX | Streamline the Settings environment | Owner: 'the whole settings environment is a mess, need to streamline it... later.' | A bigger UX/reorg pass; not started.
29 | Settings / UX | Hide unused home cards | Reorderable home cards are live. | Optional follow-up: let users hide cards they don't use. Not built.
30 | Settings / UX | index.html size / architecture review | The single ~22k-line index.html keeps growing. | Deliberate keep-single-file vs light-split/build decision; queued for strategy mode; any split must preserve the no-build Cloudflare Pages deploy.
31 | Payments / Billing | Payments + pricing model | Accept card transactions and design a location-billed seats x feature-gates + per-tier AI-allowance model on greenfield Stripe. | In planning; docs/plan-payments.md drafted awaiting approval, then build dev-first.
32 | Payments / Billing | Billing activation | Round-1 billing shipped to prod dormant (BILLING_ENABLED off). | Apply migration 0025 to prod + set up LIVE-mode Stripe before flipping BILLING_ENABLED (then ENFORCE_TRIAL).
33 | Payments / Billing | Subscription field-model code finishers | Two code finishers to land with Payments. | Stop reading franchise subscription_tier as an access grant; write 'free' (not null) in provisionNative.
34 | Payments / Billing | Trial-expiry UX questions | Parked: what happens at 14-day trial end, messaging, lockout, re-enable without losing settings. | Code read suggests ENFORCE_TRIAL is currently false and settings persist; verify before answering definitively.
35 | Auth / Session | Truly-dead session 'Reconnecting...' banner | Silent auto-refresh is live for the stale-but-refreshable case. | Deferred: a soft 'Reconnecting...' banner + one-tap re-auth for the rare truly-dead session.
36 | Auth / Session | Harden crewlogic-trucks caller verification | Per-request caller verification is deferred because Google-OAuth owners have no Supabase JWT. | Folded into future unified-auth work; residual risk low.
37 | Auth / Session | 'Name your workspace' mis-route check | The workspace-naming trap got a clearer label (live). | Low-priority: investigate whether a fully provisioned account can mis-route there via a profile-lookup edge case.
38 | Auth / Session | Native toolbar-fix prod promote | The native-estimate reopen toolbar bug is fixed and owner-verified on dev. | Pending prod promote.
39 | Multi-tenant / Time zones | Generalize Eastern-hardcoded date logic | The dispatcher is tz-aware now, but two spots stay Eastern-hardcoded. | crewlogic-todays-workorders day-window + crewlogic-job-plan nowET; apply the existing tz pattern before any non-ET franchise relies on them.
40 | Multi-tenant / Time zones | Onboarding: capture location + confirm timezone | Have the franchisee enter full office location and confirm their IANA timezone at onboarding (cost_settings.officeTimezone). | Not started; until then each non-ET franchise needs a manual officeTimezone backfill.
41 | Infra / Deploy | Reconnect crewlogic-marketing Pages Git | A Cloudflare account change left the Pages projects Git-disconnected; crewlogic is reconnected. | crewlogic-marketing (crewlogicai.com) likely still needs the same Git reconnect.
42 | Infra / Deploy | Retire the last n8n dependency | Only the route-optimization engine still runs in n8n. | Retiring it is tied to the Route Optimizer re-architecture.
43 | Infra / Deploy | Estimate-charges normalization (Phases 4-5) | Line items still live in the payload.charges JSON blob; normalization tables + dual-write are dev-only. | Apply migrations 0012+0013 + deploy dual-write to prod, then cut reads over (Phase 4) and retire the blob (Phase 5).
44 | Infra / Deploy | Storage headroom / STORAGE_INCLUDED_GB | Prod is on Supabase free tier and the secret isn't set, so the usage dashboard defaults to 1 GB. | Set the prod secret to 100 when moving to Supabase Pro; watch estimate-photo storage as testers onboard.
45 | Infra / Deploy | estimate-photos per-franchise path scoping | RLS is enforced, but per-franchise storage path scoping is deferred. | A fuller cross-tenant test suite also remains as a Phase 3 RLS follow-up.
46 | Security | Rotate + strip committed API keys | docs/Route Optimization.json embeds live Google Maps, Anthropic (x2), and Motive keys. | Rotate the exposed keys and strip the file (HEAD removal is the ceiling on this private repo).
47 | Security | Google Cloud credentials cleanup | Consolidate all CrewLogic Google keys/OAuth clients into one project and delete the unused sprawl. | Not started (inventory done); referrer/IP-restricted keys, repoint secrets, proxy Street View through an edge fn.
48 | Analytics | Track Photo-Analyzer volume-tier adjustments | Record when a user bumps an estimate up/down a tier after the AI Photo Analyzer, to measure and correct its bias. | Not started; plan first (usage_events vs dedicated table, AI-only scope, store raw suggested CY?).
49 | Analytics | Deferred usage-metering events | Metering is live, but Street View metering (needs the server proxy) and price.lookup/estimate.created events were deferred. | These extend the billing/cost backbone.
50 | Provisioning validation (QA) | Live Vonigo-connect prod validation | The two @junkluggers.com provisioning cells (invite + marketing) were never run end-to-end in prod. | Validate on a real onboarding: user -> Vonigo-pending profile -> enter creds -> franchise attaches under the JL tenant with no paywall (marketing cell carries the 14-day clock).
51 | Provisioning validation (QA) | Confirm-email deliverability re-test | DMARC is added (SPF/DKIM pass), fixing junk-foldering. | A real signup re-test to confirm inbox delivery; a custom Supabase auth domain stays deferred (paid).